## Tenders
Sr. No | Organization | City | A/c owner | Tender Details | Candidate volumes | Contract period (Years) | Pre Bid meeting date | Last date of Pre bid query submission | Last Date of Bid Submission | Tech Opening | Tech Presentation | Venue visit | Commercial Opening | QCBS | MSME Pref | Tender Fees | EMD | Status | Remarks | Tender Concerns | PO received | Agreement signed (Y/N) | PBG % | Rajan remarks | Chintan remark | Paresh Remark | Contract Value
1 | JIPMER | Pondicherry | Anbarasu | conduct of online computer-based tests (CBT) for recruitment of various posts and admissions to various academic courses of JIPMER, Puducherry for a period of TWO Years | 10000-20000 | 2+1 |  |  | 16th Feb 2026 |  |  |  |  | QCBS 70:30 |  | 1180 | 200000 | Tender getting cancelled | client kept this on hold
2 | IIBF | Mumbai | Ashish | Request for Proposal (RFP) to Select a Service Provider/s to conduct online Examinations of the Institute across India |  | 5+2 |  |  | 22nd Jan 2026 |  |  |  |  | L1 |  | 0 | 1000000 | Submitted | Tender cancelled
3 | SSC | Delhi | Prashant | EOI -Exploring Technologies to Conduct Examinations in Digital Mode |  |  |  |  | 17th March 2026 | [6 empty] | 0 | 0 | submitted | Demo date - 30th April 26 | awaiting tender
4 | DGT | Delhi | Vineet | EOI -Selection of Service Provider to Conduct End-to-End Computer Based Test and Engineering Drawing Examination for various schemes of Directorate General of Training | 14 lakhs exams |  |  |  | 30th April 2026 | [6 empty] | 0 | 0 | Submitted | submitted | awaiting the tender for shortlisted vendors - TCS/Aptech/ Eduquity /DEXIT shortlisted
5 | Odisha Univ of Agriculture | Bhubaneshwar | Deepak | RPF for conduct of Entrance Exam | 40000 + 1500 | 3 |  |  | 25th March 2026 |  |  |  |  | QCBS 70:30 |  | 5000 | 500000 | Submitted | Lost the Bid | TCS/Walrus/DEXIT - TCS Won
6 | EDCIL | Delhi | Prashant | Budgetary quote for Tablet Exam | 200000 | 2 |  |  | 1st April 2026 | [6 empty] | 0 | 0 | Empanelment | Got the Tender
7 | Technology Development Board (TDB) with | Delhi | Prashant | Conduct of COMPUTER BASED TEST) FOR WISE-IPR (2026) | 2000-5000 | 3 | 13th April 26 |  | 27th April 2026 |  | 7th May 2026 |  | 12th May 2026 | L1 |  | 0 | 50000 | Submitted | Awaiting PO | Scope/DEXIT/Edutest - only DEXIT Qualified .
8 | Central Univ of HP | Dharamshala, | Prashant | RFP) FOR HIRING OF REMOTE PROCTORING -RP and OSM EXAMINATION SERVICES FOR CENTRE FOR DISTANCE AND ONLINE EDUCATION, (CDOE) | 20000 candidates per exam cycle | 3 |  |  | 18th April 2026 |  |  |  |  | QCBS ¦ 75: 25 |  | 590 | 50000 | not submitted | Not proceeding due to criteria and legal concerns | Consortium not allowed and bidder to own the software |  |  | 5%
9 | Indian Council Of Medical Research (icmr) | Pondicherry | Anbarasu | Conduct of CET for ICMR-NIVCR | 350 | 1 |  |  | 29th April 2026 |  |  |  |  | L1 | Yes | 0 | 0 | not submitted | Queries emailed to client -to attender pre-bid meeting | MSME clause, small volume
10 | Lala Ram Swarup Institute Of Tuberculosis And Respiratory Diseases | Delhi | Prashant | Request for Proposal For Identification of Bidder(s) To conduct Computer Based Test (CBT) For National Institute of Tuberculosis & Respiratory Diseases (NITRD) | 500 | 1+4 |  |  | 27th April 2026 |  |  |  |  | QCBS |  | 0 | 150000 | Submitted | Submitted | Under Tech Evaluation |  |  | 5%
11 | EDCIL | Delhi | Prashant | EMPANELMENT OF AGENCIES IN CONTEXT OF DIGITAL EVALUATION SYSTEM OF ANSWER BOOKS (On Screen Marking) FOR VARIOUS CLIENTS OF EdCIL | 2000000 | 2+1+1 | 15th April 2026 |  | 19th May 2026, 1:00pm |  |  |  |  | L1 |  |  | 650000 | not submitted | not submitted | OSM proofs reqd; OSM partner not meeting eligiblilty criteria |  |  | 5%
12 | MP Open Univ | Bhopal | Deepak | Online/Digital Evaluation of Answer Scripts |  | 3 | 21st April 2026 |  | 30th April 2026 |  |  |  |  | QCBS ¦70:30 |  | 5000 |  | not submitted | under process | Awaiting client response - concerns on criteria reg PSU vendor
13 | IISC | Bangalore | Anbarasu | LMS for Cyber Security | 10000+ | 1 |  |  | 22nd April 2026 | [6 empty] | 0 | 0 | not submitted | not proceeding as CL cannot provide the solution | not proceeding as CL cannot provide the solution
14 | NIOS | Noida | Prashant | LMS for Training on AI |  | 5 |  |  | 23rd April 2026 | [7 empty] | 1000000 | not submitted | not proceeding as CL cannot provide the solution | not proceeding as CL cannot provide the solution
15 | Rural health Training center | Delhi | Prashant | Conduct of CBT - | 1200 | 5 month |  |  | 24th April 2026 | [6 empty] | 0 | 0 | not submitted | Queries emailed to client | MSME clause, small volume
16 | Directorate of Teacher Education (TE) & State Council of Educational Research & Training (SCERT), Odisha | Bhubaneshwar | Deepak | selection of a Service Provider for conducting Online Computer-Based Test (CBT) examinations for admission into teacher education programmes (D.El.Ed). | 120000 | 2 years | 23rd April 26 |  | 6th May 2026 | [6 empty] | 5600 | 600000 | Submitted | Lost the Bid | DEXIT/ Aptech - Aptech won
17 | NIELIT | Delhi | Prashant | Conduct of exam using NIELIT Software | 150000+ | 1+1 | 23rd April 26 |  | 12th May 2026 | [7 empty] | 1433700 | not submitted | not submitted | Profitable clause - last 3 years
18 | South Central Railway |  |  | Conduct of CBT - | [13 empty] | Tender getting cancelled | Tender cancelled
19 | Digital Univ Kerela | Thiruvananthapuram | Anbarasu | RFP FOR CONDUCTING AI AND HUMAN PROCTORED ONLINE TESTS FOR DUAT AND DRAT ENTRANCE TEST OF DUK | 500 | 1 | 28th April 2026 |  | 7th May 2026 | [6 empty] | 710 | 3000 | not submitted | not submitted | Consortium not allowed
20 | EDCIL | Delhi | Prashant | Empanelment of Service Providers for conduct of Tablet Based Digital OMR Test For Various Clients of EdCIL | 200000 | 2+1+1 | 27th April 2026 |  | 19th May 2026, 1:00pm | 26th May, 15:00hrs |  |  |  | QCBS |  | 8000000 |  | Submitted | Submitted | Under Tech Evaluation - Vensysco / DEXIT - Demo on 22nd July
21 | MP board of secondary education | Bhopal | Ashish | Tender for Digital Evaluation System |  | 3 |  |  | 12th May 2026 | [6 empty] | 50000 | 800000 | not submitted | not submitted | OSM proofs reqd; OSM partner not meeting eligiblilty criteria
22 | IIFT | Delhi | Ashish | Tender for Registration Portal and CBT | 1000 | 1 |  |  | 4th April 2026 | [5 empty] | Yes L1+15% |  | 16000 | not submitted | not submitted | clear pref for MSME
23 | IIT Madras- NPTEL | chennai | Anbarasu | Price bid for 10th May drive | 8800 | 2 months |  |  | 1st May 2026 | [7 empty] | 200000 | Submitted | Won the bid | WO received
24 | DAE- Mumbai | Mumbai | Ashish | tender for end-to-end conduct of Computer-Based Online Examination (CBT) for recruitment of JPA/JSK posts | 50000 | 3 |  |  | 28th May 2026 | [7 empty] | 1000000 | Tender getting cancelled | Tender cancelled
25 | IIBF | Mumbai | Ashish | Select a Service Provider to Conduct Hosted model Internet Based Online Examinations of the Institute Across India | 150000 | 5 | 13th May 2026 |  | 28th May 2026 | [7 empty] | 1000000 | Submitted | Won the bid | Won the Tender L&T/Sify/DEXIT = | [6 empty] | 0.9
26 | BARC | Mumbai | Ashish | Tender document for Bhabha Atomic Research Centre Training School (BARC TS) All India Computer Based Online Screening Test (CBT) for recruitment of Engineering Graduates and Science Post Graduates for OCES/DGFS & induction of Engineering and Science Post Graduate for DDFS/JRF Academic programme– 2027 and 2028 | 100000 | 2 | 13th May 2026 |  | 25th May 2026 |  |  |  |  | L1 | L1+15% | 0 | 1300000 | Submitted | Lost the Bid | Under Tech Evaluation Richmind/Satvat/Scope/Aptech/Walrus/Edutest/DEXIT. Tab & Space (Richmind) was L1
27 | IIM Bangalore | Bangalore | Anbarasu | Request for Proposal for selection of Service Provider to Conduct Computer Based Admission Test (CBAT) for Indian Institute of Management Bangalore | 12000 |  | 8th May 2026 |  | 25th May 2026, 16:30hrs | 26th May |  |  |  | QCBS |  |  | 200000 | Submitted | Lost the Bid | Participants- Cyberica/TCS/Edutest/ DEXIT Lost to TCS
28 | Barkutallah univ |  |  | OSM Tender | [11 empty] | 2000 | 2400000 | not submitted | Only PSUs can participate
29 | Bharatiya Nabhikiya Vidyut Nigam Limited (BHAVINI) | Kalpakaam | Anbarasu | Tender Invited For Sl No 1 Pre Examination Phase Total number of candidates registered , Sl No 2 Examination Phase Total number of Hall tickets released , Sl No 3 Post Examination Phase total number of candidates appeared for exam , Sl No 4 Preparation of Question bank consisting of 100 questions in one set for level 1 , Sl No 5 Preparation of Question bank consisting of 100 questions in one set for level 2 , Sl No 6 Skill test for AG typing test computer literacy test , Sl No 7 Skill test for Stenographer typing test, stenography test and computer literacy test . Examination Service Examination Service Examination Service Examination Service Examination Service Examination Service Examination Service | 20000 | 1 | 8th May 2026 |  | 27th May, 15:00hrs | [5 empty] | L1+15%+RA |  | 271632 | Submitted | Tender cancelled | Under Tech evaluation (Probable Edutest/Walrus/RD inst/Dexit/Satvat) | [6 empty] | 0.6
30 | Directorate General Of Mines Safety Dgms Ministry Of Labour And Employment | Dhanbad | Vishwajeet Singh | Tender Invited For Selection of a Service Provider to design, develop, implement, operate, and maintain a secure, scalable, and government-compliant end-to-end comprehensive digital examination and certification platform for DGMS for a period | 25000 | 5 | 20th May 2026 |  | 8th June 2026 21:00hrs | [7 empty] | 500000 | Tender getting cancelled | Tender cancelled | Tender has been removed from GeM Portal
31 | Bihar Technical Service Commission (BTSC) | Patna | Vishwajeet Singh | Selection of Agency for Providing Computer Based Examination Services for Bihar Technical Service Commission (btsc). | 1500000 | 2 | 19th May 2026, 11:00hrs |  | 5th June 2026 14:00hrs |  |  |  |  | QCBS (70:30) |  |  | 1000000 | Submitted | Won the bid | DEXIT/Edutest/Eduquity/ TCS - Edutest disqualified Presentation on 19June26. DEXIT was declared H1 and won
32 | Directorate Of Purchase And Stores - Department Of Atomic Energy | Mumbai | Ashish Koul | Examination Service - Online; Question Paper Design, Candidate Registration, Payment Process to be handled by Service Provider, Provision of Venue, Update Registration, Question Paper Hosting on Website, Admit Card Proccesing, Biometric attendance of.. | 50000 | 3 | 28th May 2026,11:00hrs |  | 27th July 2026,14:00hrs |  |  |  |  | L1 | L1+15%+RA |  | 1000000 | Submitted | Submitted | Under Tech Evaluation | [6 empty] | 2.5
33 | Controller General of Accounts (CGA), Ministry of Finance | New Delhi | Prashant Sharma | Tender for conduct of Computer-Based Test (CBT) examinations for departmental examinations including the Assistant Accounts Officer (Civil) Examination | 7500 | 3 | 26th May 2026,14:00hrs |  | 9th June 2026, 13:00hrs |  |  |  |  | QCBS 70:30 |  |  | 187500 | Submitted | Submitted | Under Tech Evaluation 8 participants. Demo on 5th Aug | [6 empty] | 0.25
34 | The Assam Agricultural University (AAU) | Jorhat | Vineet Thomas | For the conduct of Computer Based Online Entrance Examination - 2026-27 | 8000 | Not mentioned | Need to check the official website for more information |  | 28th May 2026, 16:00hrs | [7 empty] | NA | Submitted | Lost the Bid | Lost on Pricing -Diversified/Nextra/Hubblebox/DEXIT
35 | Arignar Anna Zoological Park (AAZP), Chennai, Tamil Nadu Forest Department | Chennai | Anbarasu | Development of an Online Application and Registration System (OARS) for recruitment at Zoo Authority of Tamil Nadu, including candidate registration, application processing, payment gateway integration, admit card generation, helpdesk support, result processing, publication, and MIS reporting | Not mentioned | 3 months | Need to check the official website for more information |  | 17th June 2026 |  |  |  |  | L1- cut off 70 |  |  | 36000 | Submitted | Lost the Bid | 17 participants. Demo and Presentation on 27June26 Meta I = L1
36 | Indian Coast Guard | Noida | Prashant | Provision of online examination services including question paper design, candidate registration, payment processing, venue provision, registration management, question paper hosting, and admit card processing. Examination Service - Online, Question Paper Design, Candidate Registration, Payment Process, Provision of Venue, Withdrawal of Registration, Update Registration, Question Paper Hosting, Admit Card Processing | 30000 | 1 | 10th June 2026, 11:00hrs |  | 25th June 2026, 16:00hrs |  |  |  |  | L1 | L1+15%+RA |  | 475000 | Submitted | Lost the Bid | Under Tech Evaluation 8 participants. Technically disqualified
37 | Agricultural Scientists Recruitment Board (ASRB) | New Delhi | Prashant | Tender Invited For Examination Service - Online; Payment Process to be handled by Service Provider, Provision of Venue | 100000 | 2 | 16th June 2026, 15:00hrs |  | 8th July 2026, 16:00hrs |  |  |  |  | QCBS |  |  | 1200000 | did not submit | did not submit | unable to participate due to criteria limitation
38 | Acharya Harihar Post Graduate Institute of Cancer | Cuttack | Ashish | Computer based recruitment exam | 116 posts | 3 | 30th June 2026 |  | 12th Aug 2026 |  |  |  |  | L1 |  | 10000 | 100000 | not submitted | not submitted | Only PSU or Odisha Govt Empanelled allowed
39 | DGMS | Delhi | prashant | Tablet based exam | 2200 | 1 | 24th June 2026 |  | 6th July 2026 |  |  |  |  | L1+15% |  |  |  | Submitted | Won the bid | 10 participants
40 | Directorate of Public Instruction | Chattisgarh | Prashant | Selection of Agency for End-to-End Computer Based Recruitment Examination Services | 100000 | 2+1 | 1st July 2026 |  | 27th July 2026 |  |  |  |  | QCBS 70:30 |  |  | 400000 | Submitted | Won the bid | Tech presentation completed on 5thAug26, 3 participants -Scope, Vensysco, DEXIT | [6 empty] | 3.4
41 | MHCET | Mumbai | Ashish | Selection of an Agency for Conduct of Computer-Based Online Common Entrance Test (CET) and Centralized Admission Process (CAP) for State CET Cell, Maharashtra | 18 lakhs | 3+2 | 8th July 2026 |  | 27th July 2026 |  |  |  |  | QCBS 70:30 |  |  | 1,65,00,000 | not submitted | not submitted | Pre-bid queries response released
42 | Goa Public Service Commission (GPSC) | Goa | Ashish | For Implementation of Computer Based Examination System for Goa Public Service Commission (GPSC) | 10000 | 5 | 8th July 2026 |  | 3rd Aug 2026 |  |  |  |  | QCBS 70:30 |  | 3000 + 3000 | 200000 | Submitted | submitted | Tech presentation completed on 7thAug26, 4 participants -Cyberica, Nysa, Scope and DEXIT. Scope disqualified | [6 empty] | 0.5
43 | RRB | Chennai | Anbarasu | Engaging Exam Conducting Agency(s) to conduct Computer Based Test and all other related services like processing of Results and Panel etc. of Railway Recruitment Boards in connection with recruitment of various posts of 7th CPC Pay Matrix for various Centralized Employment Notifications (CENs) | 30000000 | 1 | 17th July 2026 |  | 10th Aug 2026 |  |  |  |  | QCBS 70:30 |  | 20000 | 10000000 | did not submit | did not submit | pre bid queries response not changed- tech criteria a concern
44 | NTPC | Chhattisgarh | Prashant | Hiring of Agency for Conduct of Computer Based Test (CBT) for Recruitment of Diploma Engineer Trainees (DET) and ITI Trainees (Backlog Vacancy) for NTPC Khargone, Lara & Gadarwara. | 1019 | 1 | 10th July 2026 |  | 17th July 2026 |  |  |  |  | L1 |  |  | 100000 | did not submit | did not submit | Closed bid
45 | UPCAR | Lucknow | Vishwajeet | Selection of Service Provider for Design, Development, Customization, Implementation and Conduct of Computer Based or Offline Examination and related activities for Direct Recruitment of Different Posts in UPCAR, Lucknow. | 100000 | 2 |  |  | 21st July 2026 |  |  |  |  | QCBS 80:20 |  | 5000 | 600000 | Tender getting cancelled | Tender cancelled
46 | KEONICS | Bangalore | Anand | Request for Proposal for Selection of Service Provider for the Design, Development, Testing, Commissioning and Conducting Online Computer Literacy Test (CLT) and Digital Certification System for Government Officials and Staff of Boards and Corporations of Government of Karnataka | 15000 | 3 | 15th July 2026 |  | 17th Aug 2026 |  |  |  |  | QCBS 80:20 |  |  | 8,69,400 | Submitted | Submitted
47 | AIIMS | Deogarh | Vishwajeet | Exam Suites Digital Tab System for conducting Paperless Digital Examinations | 300 tablets | 1 |  |  | 31st July 2026 |  |  |  |  | L1+ 15% |  |  | 300000 | did not submit | did not submit | during the pre bid meeting client confirmed it’s a purchase order for 300 tablets and AMC for 5 years | [6 empty] | 0.05
48 | TNPSC | Chennai | Anbarasu | Open Tender for Conducting Computer Based Test (CBT) of Examinations for Departmental and Direct Recruitment Examinations conducted by the Tamil Nadu Public Service Commission (TNPSC), Chennai | 350000 | 2 | 17th July 2026 |  | 30th July 2026 |  |  |  |  | QCBS 70:30 |  |  | 1000000 | Submitted | Diqualified | Technically disqualified for ISO 22301
49 | Protection of Plant Varieties and Farmers' Rights Authority (PPVFRA), Ministry of Agriculture & Farmers Welfare | Delhi | Prashant | End-to-end recruitment services for 16 posts including online application, CBT, result processing, and merit list preparation | 10000 | 1+1 |  |  | 14th Aug 2026 |  |  |  |  | QCBS 70:30 |  |  | 1000000 | did not submit | did not submit | Client has not changed the PSU status
50 | Directorate of Technical Education¦¦Govt. Engineering College - DOTE¦¦Government College of Engineering - Tirunelveli | Tirunelveli | Anbarasu | Supply, implementation, installation, and support of an Examination Management System Software (EMSS) comprising Curriculum Management, Programme Management, Student Data Management, and Controller of Examinations (COE) modules for end-to-end examination and academic administration | 1 | 1 |  |  | 6th Aug 2026 | [7 empty] | 3200 | did not submit | did not submit
51 | Adikavi Sri Maharshi Valmiki University (ASMVU), | Raichur | Anbarasu | End-to-end AI-enabled Digital Evaluation (On-Screen Marking) including answer script scanning & digitization, AI-based live proctoring, online/on-premise evaluation, moderation, re-evaluation, result processing, and managed services. | 3 lakhs script | 1+3 |  |  | 25th Aug 2026 | [7 empty] | 1200000 | Tender getting cancelled | Tender cancelled | Open to OEMs from Karnataka
52 | IIT Madras- GATE | Chennai | Anbarasu | CONDUCTING COMPUTER BASED TEST FOR GATE 2027 EXAMINATION | 80000 | 1 | 6th Aug 2026 |  | 20th Aug 2026 |  |  |  |  | QCBS (70:30) |  | 11800 | 1500000 | under process | under process | [7 empty] | 5
53 | BSSC | Patna | Deepak | Selection of an agency to conduct end-to-end CBT examinations for recruitment processes |  | 3+2 | 7th Aug 2026 |  | 28th Aug 2026 |  |  |  |  | QCBS (70:30) |  | 10000 | 500000 | under process | under process
54 | AWS | Delhi | Vineet | Conduct of Online Screening Test | 60000-100000 | 5+3 | 24th Aug 2026 |  | 1st Sept 2026 |  |  |  |  | QCBS (65:35) |  | 10000 | 500000 | under process | under process
55 | MRB | Chennai | Anbarasu | Online tender for selection of a system implementation partner (sip) for end-to-end recruitment services, including online application registration and conduct of computer-based test (cbt) for recruitment of medical and allied health services for government medical institutions in Tamil Nadu for a period of three (3) years. |  | 3 | 7th Aug 2026 |  | 18th Aug 2026 |  |  |  |  | QCBS (70:30) |  | 5725 | 212500 | under process | under process
56 | NTPCS |  | Prashant | Outsourcing of service for RECRUITMENT OF Executives in HR / Law/ O&M | 3000 | 6 months |  |  | 21st August 2026 |  |  |  |  | L1 |  | 0 | 0 | under process | under process | Limited Tender
57 | ICAI |  | Prashant | INTEGRATED EXAMINATION MANAGEMENT PORTAL FOR ICAI | lumpsum | 3 | 24th Aug 2026 |  | 9th Sept 2024 |  |  |  |  | QCBS (20:80) |  | 5000 | 500000 | under process | under process | Portal devpt project
58 | IIBF |  | Ashish | Selection of Service Provider(s) to Conduct Online Examinations, i.e. Computer Based Test (CBT), of the Institute in Centre-Based Mode Across India | 12 lakhs | 5+2 | 25th Aug 2026 |  | 5th Sept 2024 |  |  |  |  | QCBS (70:30) |  | 0 | 2500000 | under process | under process | [7 empty] | 30
Note on A1: user:

## Advisor contact
Sr. No | Organization | City | A/c owner | Tender Details | Candidate volumes | Contract period (Years) | Pre Bid meeting date | Last date of Pre bid query submission | Last Date of Bid Submission | Tech Opening | Tech Presentation | Venue visit | Commercial Opening | QCBS | MSME Pref | Tender Fees | EMD | Status | Remarks

## Sheet1
Sr. No. | Details | PreSales Target (number of Tenders) | Number of Tenders since 1st April 26 | Remarks
1 | Target for PreSales Tenders to be processed in 2026-27 | 150 |  | As per Abhay's mail dated 6th April26
2 | Total Number of Tenders Processed by Pre-Sales (Including tender review, preparation of pre-bid queries, corrigendum review, and communication of updates to stakeholders) |  | 39
3 | Tenders Qualified and Submitted |  | 17 | WON =2 (TDB PO awaited) Lost = 4 Client cancelled = 1 Under Evaluation =10
4 | Tenders we didn’t qualify |  | 12 | Consortium Clause for OSM/LMS, PSU Clause (prior to MKCL tie-up)
5 | Empanelment Tenders |  | 1 | Empanelled for Limited Tender
6 | Tender cancelled by Client |  | 4
7 | Tenders currently under process |  | 5
8 | Tender Target pending | 111

## Sheet2
2021-22
Total Qualified Tenders | submitted | 27
| did not participate | 38
| Cancelled | 2
| Under process | 3
| TOTAL | 70
Submitted | Won | 10
| Disqualified | 1
| Lost | 7
| Under evaluation | 5
| EOI | 1
| cancelled | 3
| TOTAL | 27
| Conversion % | 38.57%
| Success % | 37.04%

## Value Mapping Audit
Sr. No | Organization | Main Tender Detail | Mapping Status | ACV (₹ Cr) | TCV (₹ Cr) | Source Workbook | Source Sheet | Source Row | Audit / Decision Notes | Value field | Definition / mapping rule
1 | JIPMER | conduct of online computer-based tests (CBT) for recruitment of various posts and admissions to various academic courses of JIPMER, Puducherry for a period of TWO Years | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution. | ACV | Annual Contract Value: normalized annual value for a recurring/multi-year contract. For one-time / one-year awards, ACV generally equals TCV.
2 | IIBF | Request for Proposal (RFP) to Select a Service Provider/s to conduct online Examinations of the Institute across India | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution. | TCV | Total Contract Value over the stated base contract term. Optional extension years are included only when the source explicitly values them.
3 | SSC | EOI -Exploring Technologies to Conduct Examinations in Digital Mode | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution. | Primary main-sheet value | Contract Value (TCV, ₹ Cr) is populated only for high-confidence tender-level matches.
4 | DGT | EOI -Selection of Service Provider to Conduct End-to-End Computer Based Test and Engineering Drawing Examination for various schemes of Directorate General of Training | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution. | Review matches | Probable matches are documented in this audit sheet with suggested ACV/TCV but left blank in the main Tenders sheet until manually confirmed.
5 | Odisha Univ of Agriculture | RPF for conduct of Entrance Exam | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution. | Units | The structured ACV/TCV columns in the source workbook are in ₹ Cr. Narrative remarks sometimes use inconsistent labels such as '.12 L' for 0.12 Cr; structured numeric columns are treated as authoritative where match is clear.
6 | EDCIL | Budgetary quote for Tablet Exam | Review – probable match | 10 | 20 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 8 | Possible match to EDCIL Tablet Exam. Main file has 2L candidates / 2 years; source has 1L volume and value 10 Cr. Needs manual confirmation before aggregation. | No inference | We do not reverse-calculate TCV from ACV × tenure when the source does not state the TCV, and we do not value optional extensions unless the source provides that value.
7 | Technology Development Board (TDB) with | Conduct of COMPUTER BASED TEST) FOR WISE-IPR (2026) | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution. | Goal | Maximize tender-level accuracy and prevent false aggregation in the Tender Intelligence dashboard.
8 | Central Univ of HP | RFP) FOR HIRING OF REMOTE PROCTORING -RP and OSM EXAMINATION SERVICES FOR CENTRE FOR DISTANCE AND ONLINE EDUCATION, (CDOE) | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution. | Contract Value (Primary) | Uses TCV where sourced; if TCV is not stated but ACV is stated, it uses ACV and the audit sheet explicitly indicates that basis.
9 | Indian Council Of Medical Research (icmr) | Conduct of CET for ICMR-NIVCR | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
10 | Lala Ram Swarup Institute Of Tuberculosis And Respiratory Diseases | Request for Proposal For Identification of Bidder(s) To conduct Computer Based Test (CBT) For National Institute of Tuberculosis & Respiratory Diseases (NITRD) | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
11 | EDCIL | EMPANELMENT OF AGENCIES IN CONTEXT OF DIGITAL EVALUATION SYSTEM OF ANSWER BOOKS (On Screen Marking) FOR VARIOUS CLIENTS OF EdCIL | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
12 | MP Open Univ | Online/Digital Evaluation of Answer Scripts | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
13 | IISC | LMS for Cyber Security | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
14 | NIOS | LMS for Training on AI | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
15 | Rural health Training center | Conduct of CBT - | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
16 | Directorate of Teacher Education (TE) & State Council of Educational Research & Training (SCERT), Odisha | selection of a Service Provider for conducting Online Computer-Based Test (CBT) examinations for admission into teacher education programmes (D.El.Ed). | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
17 | NIELIT | Conduct of exam using NIELIT Software | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
18 | South Central Railway | Conduct of CBT - | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
19 | Digital Univ Kerela | RFP FOR CONDUCTING AI AND HUMAN PROCTORED ONLINE TESTS FOR DUAT AND DRAT ENTRANCE TEST OF DUK | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
20 | EDCIL | Empanelment of Service Providers for conduct of Tablet Based Digital OMR Test For Various Clients of EdCIL | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
21 | MP board of secondary education | Tender for Digital Evaluation System | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
22 | IIFT | Tender for Registration Portal and CBT | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
23 | IIT Madras- NPTEL | Price bid for 10th May drive | Review – probable match | 0.4266 | 0.4266 | August 26 Client Segmentation Overview.xlsx | Q1+July Buisness Development | 7 | Possible match to IITM-NPTEL May exam drive. Source says 9K candidates and 42.66L value; main file is specifically the 10 May drive. Needs confirmation that the value belongs to this exact bid.
24 | DAE- Mumbai | tender for end-to-end conduct of Computer-Based Online Examination (CBT) for recruitment of JPA/JSK posts | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
25 | IIBF | Select a Service Provider to Conduct Hosted model Internet Based Online Examinations of the Institute Across India | Mapped – High confidence | 0.9 | 4.5 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 10 | Exact match: IIBF hosted-model Internet Based Exam; 1.5L volume; 5-year term; value 90L; TCV 4.5 Cr.
26 | BARC | Tender document for Bhabha Atomic Research Centre Training School (BARC TS) All India Computer Based Online Screening Test (CBT) for recruitment of Engineering Graduates and Science Post Graduates for OCES/DGFS & inducti… | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
27 | IIM Bangalore | Request for Proposal for selection of Service Provider to Conduct Computer Based Admission Test (CBAT) for Indian Institute of Management Bangalore | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
28 | Barkutallah univ | OSM Tender | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
29 | Bharatiya Nabhikiya Vidyut Nigam Limited (BHAVINI) | Tender Invited For Sl No 1 Pre Examination Phase Total number of candidates registered , Sl No 2 Examination Phase Total number of Hall tickets released , Sl No 3 Post Examination Phase total number of candidates appeare… | Mapped – High confidence | 0.6 | 0.6 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 13 | Exact account/tender match: BHAVINI; 20K–22K volume range; 1-year term; ACV=TCV 0.60 Cr.
30 | Directorate General Of Mines Safety Dgms Ministry Of Labour And Employment | Tender Invited For Selection of a Service Provider to design, develop, implement, operate, and maintain a secure, scalable, and government-compliant end-to-end comprehensive digital examination and certification platform… | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
31 | Bihar Technical Service Commission (BTSC) | Selection of Agency for Providing Computer Based Examination Services for Bihar Technical Service Commission (btsc). | Review – probable match | 10 | 20 | August 26 Client Segmentation Overview.xlsx | Q1+July Buisness Development | 14 | Possible match to BTSC award. Source says ACV 10 Cr / TCV 20 Cr, 2+1 years, but main file has 15L candidates and 2 years. Needs confirmation.
32 | Directorate Of Purchase And Stores - Department Of Atomic Energy | Examination Service - Online; Question Paper Design, Candidate Registration, Payment Process to be handled by Service Provider, Provision of Venue, Update Registration, Question Paper Hosting on Website, Admit Card Procc… | Mapped – High confidence | 2.5 | 7.5 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 11 | Exact match: DPS/DAE examination service; 3-year term; ACV 2.5 Cr, TCV 7.5 Cr.
33 | Controller General of Accounts (CGA), Ministry of Finance | Tender for conduct of Computer-Based Test (CBT) examinations for departmental examinations including the Assistant Accounts Officer (Civil) Examination | Mapped – High confidence | 0.25 | 0.75 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 14 | Exact match: CGA CBT; 7.5K volume; 3-year tenure; ACV 0.25 Cr, TCV 0.75 Cr.
34 | The Assam Agricultural University (AAU) | For the conduct of Computer Based Online Entrance Examination - 2026-27 | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
35 | Arignar Anna Zoological Park (AAZP), Chennai, Tamil Nadu Forest Department | Development of an Online Application and Registration System (OARS) for recruitment at Zoo Authority of Tamil Nadu, including candidate registration, application processing, payment gateway integration, admit card genera… | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
36 | Indian Coast Guard | Provision of online examination services including question paper design, candidate registration, payment processing, venue provision, registration management, question paper hosting, and admit card processing. Examinati… | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
37 | Agricultural Scientists Recruitment Board (ASRB) | Tender Invited For Examination Service - Online; Payment Process to be handled by Service Provider, Provision of Venue | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
38 | Acharya Harihar Post Graduate Institute of Cancer | Computer based recruitment exam | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
39 | DGMS | Tablet based exam | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
40 | Directorate of Public Instruction | Selection of Agency for End-to-End Computer Based Recruitment Examination Services | Mapped – High confidence | 3.4 | 6.8 | August 26 Client Segmentation Overview.xlsx | Business Development Highlights | 6 | Strong match: Directorate of Public Instruction CBT; 1L volume; source says value 3.4 Cr, TCV 6.8 Cr. Main file shows 2+1; source values appear to cover the stated 2-year base term, not optional extension.
41 | MHCET | Selection of an Agency for Conduct of Computer-Based Online Common Entrance Test (CET) and Centralized Admission Process (CAP) for State CET Cell, Maharashtra | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
42 | Goa Public Service Commission (GPSC) | For Implementation of Computer Based Examination System for Goa Public Service Commission (GPSC) | Mapped – High confidence | 0.5 | 2.5 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 9 | Exact match: Goa PSC; 10K volume; 5-year tenure; ACV 0.50 Cr, TCV 2.50 Cr.
43 | RRB | Engaging Exam Conducting Agency(s) to conduct Computer Based Test and all other related services like processing of Results and Panel etc. of Railway Recruitment Boards in connection with recruitment of various posts of … | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
44 | NTPC | Hiring of Agency for Conduct of Computer Based Test (CBT) for Recruitment of Diploma Engineer Trainees (DET) and ITI Trainees (Backlog Vacancy) for NTPC Khargone, Lara & Gadarwara. | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
45 | UPCAR | Selection of Service Provider for Design, Development, Customization, Implementation and Conduct of Computer Based or Offline Examination and related activities for Direct Recruitment of Different Posts in UPCAR, Lucknow… | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
46 | KEONICS | Request for Proposal for Selection of Service Provider for the Design, Development, Testing, Commissioning and Conducting Online Computer Literacy Test (CLT) and Digital Certification System for Government Officials and … | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
47 | AIIMS | Exam Suites Digital Tab System for conducting Paperless Digital Examinations | Mapped – High confidence | 0.05 | 0.05 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 16 | Strong match: AIIMS Deoghar tablet exam; 1K candidates / 300 tablets; one-year term; ACV=TCV 0.05 Cr.
48 | TNPSC | Open Tender for Conducting Computer Based Test (CBT) of Examinations for Departmental and Direct Recruitment Examinations conducted by the Tamil Nadu Public Service Commission (TNPSC), Chennai | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
49 | Protection of Plant Varieties and Farmers' Rights Authority (PPVFRA), Ministry of Agriculture & Farmers Welfare | End-to-end recruitment services for 16 posts including online application, CBT, result processing, and merit list preparation | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
50 | Directorate of Technical Education¦¦Govt. Engineering College - DOTE¦¦Government College of Engineering - Tirunelveli | Supply, implementation, installation, and support of an Examination Management System Software (EMSS) comprising Curriculum Management, Programme Management, Student Data Management, and Controller of Examinations (COE) … | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
51 | Adikavi Sri Maharshi Valmiki University (ASMVU), | End-to-end AI-enabled Digital Evaluation (On-Screen Marking) including answer script scanning & digitization, AI-based live proctoring, online/on-premise evaluation, moderation, re-evaluation, result processing, and mana… | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
52 | IIT Madras- GATE | CONDUCTING COMPUTER BASED TEST FOR GATE 2027 EXAMINATION | Mapped – High confidence | 5 | 5 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 4 | Strong match: IIT Madras GATE 2027; 1-year term; source states approx. value 5 Cr.
53 | BSSC | Selection of an agency to conduct end-to-end CBT examinations for recruitment processes | Review – probable match | 5 | 15 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 6 | Likely BSSC match: 2L volume and 5 Cr value, but source states 3-year contract while main file shows 3+2. Do not assume optional 2-year extension value; review before using TCV in forecasting.
54 | AWS | Conduct of Online Screening Test | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
55 | MRB | Online tender for selection of a system implementation partner (sip) for end-to-end recruitment services, including online application registration and conduct of computer-based test (cbt) for recruitment of medical and … | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
56 | NTPCS | Outsourcing of service for RECRUITMENT OF Executives in HR / Law/ O&M | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
57 | ICAI | INTEGRATED EXAMINATION MANAGEMENT PORTAL FOR ICAI | Unmapped – no verified source match |  |  | August 26 Client Segmentation Overview.xlsx |  |  | No sufficiently precise tender-level match found; intentionally left unmapped to avoid false attribution.
58 | IIBF | Selection of Service Provider(s) to Conduct Online Examinations, i.e. Computer Based Test (CBT), of the Institute in Centre-Based Mode Across India | Mapped – High confidence | 30 | 150 | August 26 Client Segmentation Overview.xlsx | Significant Tender Opportunity | 3 | Exact match: IIBF CBT Recruitment Exam; 12L volume; 5-year base term; ACV 30 Cr, TCV 150 Cr. Main file shows 5+2; optional extension is not included in source TCV.